## Task Assignments
Medicine Stockout Prediction — Who's Doing What (Task List for the Group)
Group 10 ¦ Task assignments across Weeks 1-4. Update the '-' cells as work is completed.
# | Name | Role | Week 1 | Week 2 | Week 3 | Week 4
1 | Ally Juma Ngozoma | Team lead | Write problem statement | Check pipeline | Coordinate testing | Put report together
2 | Idelphonsus Buberwa Didacus | Data person | Explain the dataset | Build data cleaning steps | Help with feature stuff | Finish repo
3 | Innocent Daud | Data person | Explain synthetic data | Check train/test split | Re-run pipeline | Write data section
4 | Rejina Magembe Mase | EDA | Missing values, outliers | Help pick features | - | -
5 | Asha Bakari Seleman | EDA | Graphs and distributions | - | Error checking | Help with slides
6 | Alex Paulo Petro | Modeling | Data dictionary | Build first simple model | - | -
7 | Salmon Mkiza Thomas | Modeling | - | Get baseline numbers | Try more models, tune them | Help with demo
8 | Adrianus Mubezi Audax | Modeling | - | - | Do evaluation metrics | Put results in report
9 | Faidha Bakari Maulidi | Writing | Write up problem statement | Write README | Document tuning | Final README
10 | Joyce Evod Kauki | Writing | Write up problem statement | Write README | Document tuning | Final README
11 | Najash Bilal Jumanne | Presenting | Scope slide | - | - | Do the presentation

## Contribution Log (detailed)
Detailed Contribution Log (optional — use for peer review notes)
Member Name | Week | Task / Deliverable | Description of Contribution | Hours (approx.) | % Contribution to Task | Peer Review Notes

## Summary by Member
Contribution Summary by Member
Member Name | Role | Weeks with an assigned task
Ally Juma Ngozoma | Team lead | 4
Idelphonsus Buberwa Didacus | Data person | 4
Innocent Daud | Data person | 4
Rejina Magembe Mase | EDA | 2
Asha Bakari Seleman | EDA | 3
Alex Paulo Petro | Modeling | 2
Salmon Mkiza Thomas | Modeling | 3
Adrianus Mubezi Audax | Modeling | 2
Faidha Bakari Maulidi | Writing | 4
Joyce Evod Kauki | Writing | 4
Najash Bilal Jumanne | Presenting | 2